## Summary
DBM Portal — Build Cost (One-time)
Engineering effort × blended rate, plus design / QA / PM / contingency, plus non-labor hard costs.
Phase 1 is already shipped (greyed Done on Hours sheet). 'Remaining build' is what's left to ship Phases 2-7.
Scenario | $/hr | Eng cost | +Design/QA/PM | +Contingency | Total build
Solo / founder-built (you + AI) | 50 | 82400 | 119480 | 137402 | 143106
Offshore agency | 40 | 65920 | 95584 | 109921.6 | 115625.6
US contractor / boutique | 110 | 181280 | 262856 | 302284.4 | 307988.4
US FTE blended | 140 | 230720 | 334544 | 384725.6 | 390429.6
Build cost by phase (at solo/founder rate)
Phase | Hours | Eng cost | +D/Q/PM | +Contingency | Status
P1 — Find (search, directory) | 272 | 13600 | 19720 | 22678 | Done
P2 — Get bids | 284 | 14200 | 20590 | 23678.5 | Remaining
P3 — Compare bids | 228 | 11400 | 16530 | 19009.5 | Remaining
P4 — Sign contract | 152 | 7600 | 11020 | 12673 | Remaining
P5 — Execute contract | 448 | 22400 | 32480 | 37352 | Remaining
P6 — Close contract | 132 | 6600 | 9570 | 11005.5 | Remaining
P7 — Reviews | 132 | 6600 | 9570 | 11005.5 | Remaining
TOTAL (all phases) | 1648 | 82400 | 119480 | 137402
REMAINING (P2–P7 only) | 1376 | 68800 | 99760 | 114724
Calendar time (solo, ~30 hrs/week productive)
Remaining hours / 30 hrs per week | 45.8667 | weeks | 10.6667 | months
What's included / excluded
Included | Backend (NestJS+Prisma+Postgres), Frontend (Next.js), Mobile (Expo), 3rd-party integrations (Firebase, Claude, R2, DocuSign, Stripe Connect, Pusher, SendGrid), DevOps on Render, app-store submissions, light security review, ToS/Privacy legal.
Excluded | Ongoing hosting/opex (in separate cost model), AI usage cost (in opex), marketing/CAC, customer support, dedicated SRE, SOC 2 audit, advanced security pen test, multi-region HA, future city permit/building-rules API integration.
Future scope | Per-city integration with municipal APIs for permit/license lookup and building-code rules. Each city ≈ 60–120 hrs + possible API/data fees. Track separately when committed.

## Rates
Blended Engineering Rates ($/hour)
Edit these to flex the whole model. Three scenarios drive the Summary.
Scenario | Blended $/hr | Notes
Solo / founder-built | 50 | You + AI agents (this build). Out-of-pocket = cloud + tools only; time is opportunity cost.
Offshore agency | 40 | India / LATAM senior+mid mix. Full QA + PM included.
US contractor / boutique | 110 | US-based senior contractor blended with mid. No benefits.
US FTE blended | 140 | Loaded cost (salary + benefits + tax + tools) ÷ ~1,800 productive hours.
Multipliers
Item | Value | Notes
Design % of build | 15% | UI/UX work as % of engineering hours. Set 0 if design is bundled.
QA % of build | 20% | Manual + automated QA hours as % of engineering.
PM / coordination % | 10% | PM, standups, vendor coord, docs.
Contingency % | 15% | Risk buffer for scope creep, integrations, retries.
One-time hard costs (non-labor)
Item | $ | Notes
Apple Developer Program | 99 | Required to ship iOS / Sign in with Apple. Annual.
Google Play Developer | 25 | One-time.
Domain + email (yr 1) | 100 | Domain, Google Workspace seat, transactional sender.
Design tools (Figma yr 1) | 180 | $15/mo × 12. Skip if solo.
Logo / brand identity | 500 | One-shot Fiverr/Upwork. Skip if DIY.
Legal — ToS / Privacy / DPA | 1500 | Template + lawyer review. Required before public launch.
Security review / pen test (light) | 3000 | Pre-launch external review. Recommended pre-Phase 5.
DocuSign sandbox + setup | 0 | Free for dev. Production billed per envelope (opex).
Stripe Connect onboarding | 0 | Free; fees are passthrough (opex).
App store assets / screenshots | 300 | Per platform. Designer or DIY.
Subtotal — One-time hard costs | 5704

## Hours
Engineering Hours by Phase
Effort estimate for a senior generalist building with AI assistance. Phase 1 is already shipped (marked Done).
Phase | Module | Backend hrs | Frontend hrs | Mobile hrs | Scope / Notes
P1 | Auth & accounts (Firebase, email/Google) | 24 | 20 | 8 | Sign-up, sign-in, password reset, sessions, role gating. ✅ Shipped.
P1 | Pro directory & search | 40 | 32 | 12 | Profile model, search indexing, filters by trade/zip. ✅ Shipped.
P1 | Pro profile + portfolio uploads | 28 | 24 | 8 | Photos, services, license fields, R2 storage. ✅ Shipped.
P1 | Admin moderation basics | 16 | 12 | 0 | Flag, approve, suspend. ✅ Shipped.
P1 | Mobile shell (Expo) + deep links | 8 | 0 | 40 | Tab nav, auth, profile screens. ✅ Shipped.
P2 | Bid request flow (homeowner) | 32 | 36 | 16 | Project scope form, photo/PDF upload, location.
P2 | Bid form for pros (respond) | 28 | 28 | 12 | Line items, attachments, validity window.
P2 | AI scope scan (Claude + vision) | 40 | 16 | 0 | Parse uploaded plans, extract scope, generate checklist. Anthropic Claude.
P2 | Lead matching + delivery | 24 | 12 | 0 | Match homeowner request to qualified pros; throttle, $25/lead billing hook.
P2 | Notifications (email + push) | 20 | 8 | 12 | SendGrid email + Expo push tokens.
P3 | Bid comparison UI | 16 | 40 | 12 | Side-by-side line-item compare, totals, conditions.
P3 | Negotiation / counter-offer thread | 28 | 24 | 16 | Threaded messages, attachments, status.
P3 | Subscription billing (Stripe) | 32 | 20 | 8 | $100/mo pro subscription, plans, dunning, webhooks.
P3 | Award / select winning bid | 16 | 12 | 4 | State machine: awarded → contract draft.
P4 | Contract draft generator | 32 | 24 | 0 | Templates, variables, PDF render, e-sign-ready.
P4 | DocuSign integration | 40 | 20 | 8 | Envelopes, signers, webhook on completion, audit trail.
P4 | Take-rate billing on signed contracts | 20 | 8 | 0 | 4% platform fee captured via Stripe Connect at signature.
P5 | Schedule / milestones | 32 | 32 | 16 | Gantt-lite, dependencies, baseline vs actual.
P5 | Budget tracking & change orders | 36 | 28 | 12 | Approved budget, change orders, approval flow.
P5 | RFI / clarification thread | 24 | 24 | 12 | In-project Q&A pinned to scope items.
P5 | Progress photos & daily logs | 20 | 20 | 24 | Camera capture, geo-tag, daily reports.
P5 | Milestone payments (Stripe Connect) | 40 | 24 | 8 | Escrow-style hold, release on milestone, dispute hooks.
P5 | Real-time chat & updates (Pusher) | 28 | 24 | 16 | Websockets, presence, push fan-out.
P5 | Redis + jobs + rate limits | 24 | 4 | 0 | BullMQ workers, scan queue, lead throttle.
P6 | Punchlist & sign-off | 20 | 24 | 12 | Item list, photos, accept/reject, finalize.
P6 | Lien release & final payment | 24 | 16 | 4 | Lien waiver flow, final invoice, payout.
P6 | Project archive / closeout package | 16 | 12 | 4 | PDF bundle: contract, change orders, photos, payments.
P7 | Reviews & testimonials | 20 | 24 | 16 | Two-way reviews, moderation, public profile display.
P7 | Lessons-learned + ratings analytics | 16 | 12 | 0 | Pro reliability score, surface in search ranking.
P7 | Trust & safety (search + moderation) | 24 | 16 | 4 | Search ranking guardrails, abuse reporting.
| TOTAL Engineering Hours | 768 | 596 | 284
| GRAND TOTAL Engineering Hours | 1648