## Summary
DBM City Integration — Phased Build Cost
Wave 1: Dallas (Accela). Wave 2: Flower Mound (eTRAKiT/Shovels). Wave 3: Houston (legacy ILMS).
Cost per wave at solo/founder rate. Switch rate via the Rates sheet to see other scenarios.
Wave | Hours | Eng cost | +Design/QA/PM | +Contingency | +Hard share (= Wave total)
Wave 1 — Dallas (Accela) | 368 | 18400 | 26680 | 32016 | 35116
Wave 2 — Flower Mound | 160 | 8000 | 11600 | 15080 | 16630
Wave 3 — Houston (ILMS) | 268 | 13400 | 19430 | 27202 | 28752
ALL WAVES (v1 total, solo rate) | 796 | 39800 | 57710 | 74298 | 80498
Total v1 build by rate scenario
Scenario | $/hr | W1 cost | W2 cost | W3 cost | Total v1
Solo / founder-built (you + AI) | 50 | 35116 | 16630 | 28752 | 80498
Offshore agency | 40 | 28712.8 | 13614 | 23311.6 | 65638.4
US contractor / boutique | 110 | 73535.2 | 34726 | 61394.4 | 169655.6
US FTE blended | 140 | 92744.8 | 43774 | 77715.6 | 214234.4
Year 1 total at solo rate (build + Y1 vendor opex)
One-time v1 build (solo, all 3 waves) |  | 80498
Year 1 vendor opex |  | 24288
Year 1 total (solo) |  | 104786
Calendar time (solo @ ~30 hrs/week)
Wave 1 — Dallas | 12.2667 | weeks (~4 weeks with agents in parallel)
Wave 2 — Flower Mound | 5.3333 | weeks (~3 weeks with agents in parallel)
Wave 3 — Houston | 8.9333 | weeks (~5–6 weeks with agents in parallel)
Scale-out after v1 (marginal cost per additional city)
Next-city tier | Cities | Avg hrs | Eng cost @ solo | Notes
Another Accela city (FW, Arlington) | 5 | 32 | 8000 | Adapter exists; config + smoke + amendments only.
Another eTRAKiT city (Plano, Frisco) | 5 | 40 | 10000 | Reuse Flower Mound adapter.
Another ILMS-style legacy portal | 3 | 100 | 15000 | Different HTML each time.
Brand-new vendor | 3 | 120 | 18000 | Discovery + new adapter + tests.
Scope notes
Wave 1 — Dallas | Accela Construct API. Builds the schema, adapter interface, code framework, ops console. Roughly half the build sits here because it's the foundation.
Wave 2 — Flower Mound | Shovels.ai if it covers — verified in Discovery. Otherwise eTRAKiT portal automation. Reuses everything from Wave 1.
Wave 3 — Houston | Legacy ILMS portal automation + Houston code amendments. No zoning rules (Houston has none). Highest contingency (40%).
In v1 scope | Permit lookup (read-only) + code/rules lookup. Admin console, smoke tests, 3-city support.
Out of v1 | Electronic permit filing (write). Inspection scheduling. Mobile-app surfaces. Cities beyond Dallas/FM/Houston. SOC 2.
Vendor opex | Shown on Rates sheet — does not roll into build cost. Year 1 total includes it.

## Rates
Blended Rates ($/hour)
Same scenarios as DBM_Build_Cost.xlsx. Edit to flex the model.
Scenario | Blended $/hr | Notes
Solo / founder-built (you + AI agents) | 50 | Your time × AI subagent throughput.
Offshore agency | 40 | India / LATAM senior+mid blend.
US contractor / boutique | 110 | US senior contractor + mid.
US FTE blended | 140 | Loaded annual / 1800 productive hrs.
Multipliers (applied on top of engineering cost)
Item | Value | Notes
Design % of build | 10% | Light — admin/ops UI mostly.
QA % of build | 25% | Heavier — integration testing per city.
PM / coordination % | 10% | Vendor coordination.
Wave 1 contingency % | 20% | Dallas — Accela has docs, lower risk.
Wave 2 contingency % | 30% | Flower Mound — vendor-gated, moderate risk.
Wave 3 contingency % | 40% | Houston — legacy ILMS, high risk of surprises.
Vendor & recurring cost (annual, opex — not in build total)
Vendor | $/yr | Notes
Shovels.ai API (self-serve) | 7188 | $599/mo × 12. Only $ if it covers FM/Houston.
Accela Developer Construct API (read) | 0 | Free for citizen-scope reads (Dallas).
ICC Code Connect API (impl. + content) | 12000 | Placeholder; ICC requires quote.
UpCodes Pro reference seat | 600 | $50/mo; verification only.
Browserless / portal automation infra | 900 | Cloud headless browsers for FM + Houston portals.
Address normalization (Smarty/USPS) | 600 | Dedupe addresses across vendors/cities.
Ongoing portal-automation maintenance | 3000 | Houston ILMS especially; budget ~$250/mo.
Subtotal — Year 1 vendor opex | 24288
One-time hard costs
Item | $ | Notes
Legal review (ToS, vendor MSAs, DPAs) | 1800 | Accela, Shovels, eTRAKiT scrape, UpCodes ToS.
Insurance bump (E&O for data accuracy) | 800 | Code-rule advice exposure.
Pilot user incentives | 600 | $200 × 3 friendly users (1 per city).
ICC initial implementation fee (one-time) | 3000 | Placeholder; ICC quote needed.
Subtotal — One-time hard costs | 6200

## Wave Hours
Agent Hours by Wave
Three phased waves: Dallas → Flower Mound → Houston. Schema/code/ops costs concentrate in Wave 1.
Agent | Wave 1 — Dallas | Wave 2 — Flower Mound | Wave 3 — Houston | Total hrs | Notes
Orchestrator (you) | 32 | 16 | 24 | 72 | Specs, PR review, Accela / Shovels / Houston vendor calls
Discovery Agent | 32 | 24 | 40 | 96 | Vendor map, endpoints, portal flow, code amendments per city
Schema Agent | 56 | 0 | 0 | 56 | Internal model + JurisdictionAdapter interface; one-time
Adapter Agent | 96 | 64 | 120 | 280 | Wave 1: Accela. Wave 2: Shovels or eTRAKiT. Wave 3: ILMS portal
Code/Rules Agent | 80 | 32 | 48 | 160 | Wave 1 builds framework + Dallas; later waves add amendments
QA & Smoke Agent | 24 | 16 | 24 | 64 | Per-city smoke tests, Slack alerts, dashboard
Ops Console Agent | 48 | 8 | 12 | 68 | Wave 1 builds admin UI; later waves extend
TOTAL Hours | 368 | 160 | 268 | 796